## Slide 1
ALERT® Training and Technology Transfer Status
DEV: Yuming Liu
OPT: Emerson Chang
V2.1,
Mar 14, 2017
Notes: 7

## Slide 2: Contents
ALERT® Technology Transfer Status
  Self Assessment
  DEV/OPT Action Plan
  ALERT’s Follow-up Plan
Development Methodology
Future Work to Build Generic Solution

## Slide 3
Training & Technology Transfer

## Slide 4: Training & Tech Transfer Activities

## Slide 5: ALERT’s Comments
Training & Transfer | Summary
Training | Pre-Sales, Sales and Demos is almost 80% completed
Product Roadmap | Dedicated to CCH/YCH project tasks: Functional analysis Prototype Roadmap definition & planning Compal developers need to complete the Knowhow transfer and certificated by ALERT's experts, then join the CCH project development
Knowhow Transfer | 55~60% completed, needs 3.5~4 months to finish the KhT program

## Slide 6: Self Assessment (by Product)
 | DEMO | DEV
ALERT@PFH |  | 
ALERT®TRIAGE | 100% | 50%
ALERT®EDIS | 77% | 65%
ALERT®OBS | 0% | 
ALERT®AMBULATORY | 60% | 50%
ALERT®WAITING ROOM | --- | ---
ALERT®OUTPATIENT | --- | 50%
ALERT®INPATIENT | 83% | 65%
ALERT®PRESCRIPTION | 0% | 45%
ALERT®DECISION TREE | 10% | 10%
ALERT®ORIS | 70% | 55%
ALERT®CANCER INFO-SYS | 0% | n.a.
ALERT®PRIMARY CARE | 13% | 50%
ALERT®PRIVATE PRACTICE | 10% | 50%
ALERT®REFERRAL | 10% | 30%
ALERT®HOME VISIT | --- | ---
ALERT®PDMS | 50% | 3%
ALERT®PHARMACY | 20% | 40%
ALERT®GP PORTAL | --- | ---
ALERT®eLEARNING | 10% | 0%
ALERT®STANDARD CONTENT | 0% | 70%
INTER-ALERT® | 0% | 70%
EMR
 | DEMO | DEV
ALERT®ADT | 17% | 17%
ALERT®SCHEDULER | 10% | 3%
ALERT®CODING | 0% | 0%
ALERT®PATIENT PORTAL | --- | ---
ALERT®CRM | --- | ---
ALERT®BILLING | --- | ---
ALERT®DATA WAREHOUSE | 0% | 0%
ALERT®BI | 43% | 0%
ALERT®PLANING SYSTEM | 10% | 0%
ALERT®AUDIT TRAIL | 0% | 0%
ALERT®HIE | 13% | 0%
ALERT®MyALERT | 37% | 0%
ALERT®STUDENT | 0% | 0%

## Slide 7: Self Assessment (by Tech Func)
 | Func Activities Func Team | Training Days | Self Assessment | Comments
 | Function Analysis | 1 | 80% | Better to co-work with ALERT teams
 | Product Design | 1 | 80% | Better to co-work with ALERT teams
 | Flash | 44 | 80% | Few documents, need to trace source code
 | PL/SQL | 23 | 90% | KhT didn’t cover all of PL/SQL programs,
 | Content Creation | 4 | 75% | 10% docs need translation, need APEX tool
 | Content Configuration | 2 | 70% | KhT didn’t include whole contents in ALERT system
 | Versioning | 5 | 70% | Not sure the exact version of source code on SVN
 | Java | 5 | 30% | Scope of KhT is not confirmed yet
 | Integration | 10 | 70% | Need to add ‘Data mapping’ & ‘Data migration’
 | PM | 9 | 100% | ALERT hasn’t provided development schedule
 | Implementation | 15 | 87% | Need ALERT to provide a new template creation tool
 | QA | 0 | 30% | KhT QA course is under arragement
 | Configuration | 9 | 58% | 20-30% unexpected troubleshooting & checklist
 | System IT | 18 | 92% | Need configuration of Crisis machine & NOC Tools
Development Team
Operation Team

## Slide 8: Self Assessment (by Source Code)
Product | DEV | # of Source Code |  |  | Summary
 |  | UI | Java | Database | 
ALERT® TRIAGE | 50% | 106 | 37 | 3,055 + 26,587 (DDL/DML) | Understood, need real practice
ALERT® EDIS | 65% | 229 | 238 |  | Understood, need real practice
ALERT® INPATIENT | 70% | 136 | 358 |  | Understood, need real practice
ALERT® ORIS | 55% | 59 | 394 |  | Understood, need real practice
ALERT® AMBULATORY | 50% | 216 | 7,425 |  | 
ALERT® PRIMARY CARE | 50% | 216 | 7,425 |  | Based on ALERT® AMBULATORY
ALERT® PRIVATE PRACTICE | 50% | 216 | 7,425 |  | Based on ALERT® AMBULATORY
ALERT® REFERRAL | 30% | 93 | 537 |  | 
ALERT® DECISION TREE | 10% | 24 | n.a. |  | Not in KhT
ALERT® OBS | 0% | --- | --- |  | No Source code
ALERT® CANCER INFO-SYS | 0% | --- | --- |  | No source code
ALERT® PHR (MyALERT) | 0% | JAVA: (S: 1,024) (M: 10,458) |  |  | Not trained in KhT
ALERT® eLEARNING | 0% | Java: 7,063 |  |  | Not trained in KhT
ALERT® STUDENT | 0% | Java: (S: 139) (M: 10,695) |  |  | Not trained in KhT
UI core files: 5,681

## Slide 9: Self Assessment (by Source Code)
Product | DEV | # of Source Code |  |  | Summary
 |  | UI | Java | Database | 
ALERT® ADT | 17% | 286 | 6,677 | 15 + 2,756 | Not trained in KhT
ALERT® SCHEDULER | 3% | 698 | 5,019 | 8 + 1,196 | Using FLEX, not trained in KhT
ALERT® HIE | 0% | n.a. | 6,834 | 50 + 1,055 | Not Trained in KhT
ALERT® BI | 0% | n.a. | n.a. | 0 + 35 | Not trained in KhT
ALERT® PDMS | 3% | 1,160 | 1,839 | 9 + 379 | Using FLEX, not trained in KhT
ALERT® PLANNING SYSTEM | 0% | 387 | 5,019 | n.a. | Using FLEX, not trained in KhT
ALERT® ADW | 0% | n.a. | n.a. | 0 + 35 | Not trained in KhT
ALERT® PHARMACY | 40% | 24 | 8 | 26 + 66 | 
ALERT® PRESCRIPTION | 45% | 485 | 1,474 | 169 + 2,597 | Medicine prescription in PFH
INTER-ALERT | 70% | n.a. | 6,727 | 78 + 871 | 
ALERT® AUDITTRAIL | 0% | 215 | 25 | 4 + 35 | Using FLEX, not trained in KhT
ALERT® CODING | 0% | n.a. | 5,737 | 96 + 470 | Not trained in KhT
ALERT® STANDARD CONTENT | 60% | n.a. | n.a. | 3,061 + 29,262 | Default content

## Slide 10
Follow-Up Plan

## Slide 11: Action Items (Dev Team)
Get missing documents and tools from Alert
Setup a complete development environment
Get complete source files
Build and verify the source files completeness
Setup Dev, QC servers for actual project development

## Slide 12: Action Plan (OPT Team)
01
02
03
04
2017
05
06
07
08
09
10
11
12
09
10
11
12
2016
User requirements &
Gap analysis
Implementation
Testing
Training
Content Collection
Content Creation & Validation
Test Scripts & Test
Training Scripts
On-site training
Test Plan
UAT
CCHIPD
Configurations (KhT)
Configuration (CCH)
System IT (KhT)
System IT (CCH)
NZD
NOC

## Slide 13: ALERT’s Follow-Up Plan
ALERT’s Knowhow Transfer Follow-up Planning: (within 4 months)
New Configuration tool is ready, the tool includes:
  Facility management
  Standard edition management
  Product management
  Content management
ALERT assigns 16 engineers for the development of CCH project
ALERT suggests having Compal 2~3 resources to work in Portugal with ALERT team for 2~3 weeks to learn the support skills by real case studies
ALERT will support training material and product brochure by request

## Slide 14
Development Methodology

## Slide 15: Development Phases
Functional analysis
Design
Code development
Content creation and configuration
Acceptance testing
Versioning
Quality control
Feature spec doc
Acceptance test criteria
Prototype design & flow document
UI artwork
Technical design doc
UI test case and report
Content config. files
Test Report
Performance test report
Build release report
Test plan
Test case
Test Report
Developing a new feature Feature development phases & doc outputs

## Slide 16: SW Development Process Improvements
Simplify content creation/configuration process
Simplify and automate the versioning process
Add/Enforce unit test process
Add/Enforce code review process
Other items to be identified during process execution

## Slide 17
Future Work

## Slide 18: Build a Generic Solution
In 1st project, make the capability and maturity on ALERT® PFH Solution to reach at least 80%
Finish know-how transfer 100% by end of 2017
Setup a generic version for Taiwan EMR market
Template tool for customer to simulate template requirement
Config. tool for customer to edit content and other configurations
Provide tool or simpler method for customer to edit the documentation format to reduce maintenance efforts
Add new functionalities to fit general requirements for hospitals in Taiwan, for example
  Family tree edit and display in graphical format
  Integrate with BI solution other than MicroStrategy
  Make the documentation blocks to be customizable by client
  Leverage HIE to exchange medical data between facilities
  Keep improving development process and methodology